## Sheet1
Project Management Controller_Cost Estimate
Prepared by: Venkata Sai Krishna Dasari | Date: | 2019-05-24
| # Units/Hrs. | Cost/Unit/Hr. | Subtotals | WBS Level 1 Totals | % of Total
WBS Items
1. Project Management |  |  |  | 488200 | 39.9%
1.1 Project manager | 740 | 85 | 72200
1.2 Project team members | 1510 | 70 | 120000
Contractors (10% of software development and testing) |  |  | 296000
2. Hardware |  |  |  | 48600 | 3.972%
2.1 Handheld devices | 75 | 410 | 29400
2.2 Servers | 5 | 3220 | 19200
3. Software |  |  |  | 348970 | 28.52%
3.1 Licensed software | 75 | 110 | 8970
3.2 Software development* |  |  | 340000
4. Testing (10% of total hardware and software costs) |  |  | 39757 | 39757 | 3.249%
5. Training and Support |  |  |  | 94125 | 7.693%
5.1 Trainee cost | 65 | 265 | 20625
5.2 Travel cost | 15 | 445 | 4500
5.3 Project team members | 1160 | 50 | 69000
6. Reserves (20% of total estimate) |  |  | 203930.4 | 203930.4 | 16.67%
Total project cost estimate |  |  |  | 1223582.4

## Sheet2
* Software development
Contractor labor estimate | 1500 | 120 | 192000
Project team member estimate | 1200 | 90 | 108000
Total labor estimate |  |  | 300000
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 9 | 4 | 32
External interface files | 3 | 6 | 18
External outputs | 3 | 4 | 12
External queries | 3 | 3 | 9
Logical internal tables | 4 | 8 | 32
Total function points |  |  | 103
Java 2 languange equivalency value |  |  | 46
Source lines of code (SLOC) estimate |  |  | 4738
Productivity *KSLOC^Penalty (person months) | 20.2401
Total labor hours (140 hours/month) | 2428.814
Cost/labor hour ($110/hour) | 120
Total software development estimate | 291457.6812